## Milestones
WQM Project — Milestones
Status | Milestone | Description / Deliverables
Incomplete | M1 — Project Scoping & Requirements | Define functional/non-functional requirements; identify deployment sites (Beas, Uhl, Suketi); establish sensor parameter targets and CPCB/IS-10500 thresholds.
Incomplete | M2 — Sensor Procurement & Characterisation | Procure DFRobot pH (SEN0161), Turbidity (SEN0189), TDS, DS18B20 temp, DO & Conductivity sensors; perform bench-top calibration and document accuracy baselines.
Incomplete | M3 — Edge Firmware (STM32) Development | Implement ADC-driven sensor reads, median filtering, calibration offsets, deep-sleep scheduling (5-min wake cycle), and LoRa SX1278 TX packet framing on the STM32F405.
Incomplete | M4 — Gateway Firmware (ESP32) Development | Develop LoRa SX1278 RX listener, packet validation, JSON serialisation, and SIM7600E 4G LTE HTTPS uplink on the ESP32 gateway.
Incomplete | M5 — LoRa Communication Validation | Perform range testing (2 km LoS, 500 m NLoS) with configurable Spread Factors (SF7–SF12); verify packet delivery ratio and checksum integrity in valley terrain.
Incomplete | M6 — Power System Integration | Assemble 6V/3W solar panel, CN3791 MPPT charge controller, and 3.7V 3000 mAh 18650 LiPo cell; validate ≥48 hrs autonomous operation without solar input.
Incomplete | M7 — Buoy Enclosure & Mechanical Build | Fabricate 110 mm PVC buoy with sealed end-caps, marine silicone, foam collar, and cable glands; pass IP67/submersion testing.
Incomplete | M8 — Gateway Enclosure & Shore Deployment | Mount ESP32 gateway in IP65-rated ABS junction box with 4G antenna; install pole-mount at shore-side relay point.
Incomplete | M9 — Firebase Cloud Backend Setup | Provision Firebase Firestore with Data-Bucketing schema (daily aggregate docs); implement Cloud Functions for data ingestion, validation, and WQI computation.
Incomplete | M10 — LSTM WQI Prediction Model | Train 2-layer LSTM (64→32 units, 0.2 dropout) on CPCB historical data; deploy 24-hr-ahead WQI forecasting via Firebase Cloud Functions.
Incomplete | M11 — Prophet Seasonal Trend Model | Configure Facebook Prophet for long-term seasonal decomposition and changepoint detection; integrate weekly/monthly trend reports into the backend pipeline.
Incomplete | M12 — React Dashboard — Core UI | Scaffold React 18 (Vite) SPA; build real-time time-series charts (Recharts) and geographic heatmaps (Leaflet.js) subscribed to Firestore live feeds.
Incomplete | M13 — Alert & Notification System | Implement Twilio API integration for SMS and WhatsApp alerts; configure threshold-monitoring Cloud Functions against IS-10500/CPCB norms for auto-dispatching.
Incomplete | M14 — End-to-End System Integration | Connect all layers (buoy → gateway → cloud → dashboard → alerts); run full telemetry pipeline with live sensor data and confirm data fidelity.
Incomplete | M15 — Field Deployment & Validation | Deploy buoy(s) in target Himalayan river(s); conduct ≥7-day unattended field trial; validate prediction accuracy, uptime, and alert responsiveness.
Incomplete | M16 — Performance Optimisation & Hardening | Optimise edge power draw, LoRa duty-cycle compliance, Firestore read/write costs, and ML inference latency; harden firmware OTA update path.
Incomplete | M17 — Documentation & Knowledge Transfer | Deliver complete hardware BOM, firmware source, cloud architecture docs, ML model cards, dashboard user guide, and maintenance SOP to stakeholders.